## Sheet1
Program | Resources and Requirements Match | Demonstrates All Critical Technologies in a Relevant Environment | Demonstrate all Critical Technologies in a Realistic Environment | Complete Preliminary Design Review | Product Design is Stable | Release at least 90 percent of design drawings | Test a system-level integrated prototype | Manufacturing Processes Are Mature | Demonstrate Critical processes are in control | Demonstrate Critical Process on a pilot production line | Test a production-represenative prototype
AGM-88E Advanced Anti-Radiation Guided Missile (AARGM) |  | T | T | T |  | T | T |  | F | T | T
Air and Missle Defense Radar (AMDR) |  | T | F | T |  | N/A | N/A |  | N/A | N/A | N/A
Apache Block IIIA Remanfucature Project (AB3A) |  | T | T | T |  | T | T |  | F | T | T
Army Integrated Air and Missisle Defense (ARMY IAMD) |  | T | F | T |  | N/A | N/A |  | N/A | N/A | N/A
B-2 Extremely High Frequency SATCOM Capability, Increment 1 |  | T | T | T |  | T | T |  | N/A | N/A | N/A
BMDS: Aegis Ashore |  | T | F | T |  | T | F |  | N/A | N/A | N/A
BMDS: Aegis Ballistic Missle Defense Standard Missile-3 Block IB |  | T | F | T |  | T | F |  | N/A | N/A | N/A
BMDS: Aegis Ballistic Missle Defense Standard Missile-3 Block IIA |  | F | F | F |  | N/A | N/A |  | N/A | N/A | N/A
BMDS: Ground-Based Midcourse Defense (GMD) |  | T | F | T |  | T | T |  | IN/A | IN/A | F
BMDS: Terminal High Altitude Area Defense (THAAD) |  | T | T | T |  | T | T |  | IN/A | IN/A | T
C-130 Avionics Moderniziation Program (AMP) |  | T | T | T |  | T | T |  | N/A | T | T
CH-53K - Heavy Lift Replacement |  | T | F | T |  | T | F |  | N/A | N/A | N/A
CVN 78 Class |  | F | F | T |  | T | N/A |  | N/A | N/A | N/A
DDG 1000 Destroyer |  | T | F | T |  | T | N/A |  | N/A | N/A | N/A
E-2D Advanced Hawkeye (E-2D AHE) |  | T | T | T |  | T | T |  | N/A | T | T
Excalibur Precision Guided Extended Range Artillery Projectile |  | T | T | T |  | T | T |  | N/A | N/A | N/A
F-35 Lightning II (Joint Strike Fighter) |  | F | F | T |  | T | T |  | F | T | T
Family of Advanced Beyong Line-of-Sight Terminals (FAB-T) |  | T | T | T |  | T | T |  | N/A | N/A | N/A
Global Hawk (RQ-4A/B) |  | T | T | T |  | T | N/A |  | T | T | T
Global Positioning System (GPS) III |  | T | N/A | T |  | T | F |  | T | F | F
GPS III OCX Ground Control Segment |  | T | F | T |  | N/A | N/A |  | N/A | N/A | N/A
Gray Eagle Unmanned Aircraft System |  | T | F | T |  | T | T |  | F | T | T
HC/MC-130 Recapitalization Program |  | T | T | T |  | T | N/A |  | T | F | IN/A
Integrated Defensive Electronic Countermeasures (IDECM) Block 4 |  | T | T | T |  | T | T |  | N/A | N/A | N/A
Joint Air-to-Ground Missile (JAGM) |  | T | F | T |  | N/A | N/A |  | N/A | N/A | N/A
Joint Air-to-Surface Standoff Missile Extended Range (JASSM-ER) |  | T | T | N/A |  | T | T |  | F | T | T
Joint High Speed Vessel (JHSV) |  | T | T | T |  | T | N/A |  | N/A | N/A | N/A
Joint Land Attack Cruise Missile Defense Elevated Netted Sensor System (JLENS) |  | T | F | T |  | T | T |  | N/A | N/A | N/A
Joint Precision Approach and Landing System (JPALS) |  | T | F | T |  | T | F |  | N/A | N/A | N/A
Airborne and Maritime/Fixed Station Joint Tactical Radio System (AMF JRTS) |  | T | F | T |  | T | T |  | N/A | N/A | N/A
Joint Tactical Radio System (JTRS) Handheld, Manpack, and Small Form Fit (HMS) |  | F | F | T |  | T | T |  | F | F | T
KC-46 Tanker Modernization Program |  | T | F | F |  | N/A | N/A |  | N/A | N/A | N/A
LHA Replacement Amphibious Assault Ship |  | T | T | T |  | F | N/A |  | N/A | N/A | N/A
Littoral Combat Ship (LCS) |  | T | F | T |  | T | N/A |  | N/A | N/A | N/A
Littoral Combat Ship-Mission Modules |  | IN/A | IN/A | T |  | N/A | N/A |  | N/A | N/A | N/A
Mobile User Objective System (MUOS) |  | T | N/A | T |  | T | N/A |  | N/A | F | N/A
MQ-4C Broad Area Maritime Surveilane (BAMS) Unmanned Aircraft System (UAS) |  | T | T | T |  | T | F |  | N/A | N/A | N/A
Navy Multiband Terminal (NMT) |  | T | T | T |  | T | T |  | F | T | T
P-8 Poseidon |  | T | T | T |  | T | T |  | T | T | T
Reaper Unmanned Aircraft System |  | T | T | T |  | T | F |  | N/A | N/A | N/A
Ship to Shore Connector (SSC) |  | T | T | T |  | N/A | N/A |  | N/A | N/A | N/A
Small Diameter Bomb (SDB) Increment II |  | T | F | T |  | T | F |  | N/A | N/A | N/A
Space Based Infared System (SBIRS) High Program |  | T | N/A | T |  | T | N/A |  | IN/A | F | N/A
Space Fence |  | T | F | T |  | N/A | N/A |  | N/A | N/A | N/A
Standard Missile-6 (SM-6) Extended Range Active Missile (ERAM) |  | T | T | T |  | T | T |  | F | T | T
Vertical Take-off and Landing Tactical Unmanned Aerial Vehicle (VTUAV) |  | T | T | T |  | T | T |  | IN/A | T | T
Warfighter Information Network-Tactical (WIN-T) Increment 2 |  | T | T | T |  | IN/A | T |  | F | T | T
Warfighter Information Network-Tactical (WIN-T) Increment 3 |  | T | F | T |  | N/A | N/A |  | N/A | N/A | N/A